# Siteline PRD

Siteline triages a site's redlined clinical trial agreement against the sponsor's playbook in minutes, routes escalations to approvers by text or call, and exports a counter-proposal. The HackHarvard demo ships on Devpost by Oct 18, 2026 at 8:00 AM.

## Problem and Users

Sponsors negotiate one clinical trial agreement with dozens of sites, and each site returns its own redline. Contract staff review every change by hand, even the ones the playbook already answers. Across 61 cancer centers, study start-up took a median of 167 days against a 90-day target, and slower activation is linked to missed enrollment goals (Contemp Clin Trials Commun 2025).

| User | Need | How Siteline helps |
| --- | --- | --- |
| Contract manager (primary) | Close many site agreements fast without bad terms | Upload a redline, review a decision list, export a counter-proposal |
| Approvers in legal, finance, privacy | Decide only what needs them | One text or call per escalation; reply 1, 2 or 3 |
| Study start-up lead | See which sites block activation | Portfolio radar of days open and stuck clauses |

## Goals, Non-Goals and Success Metrics

Goals:

- Triage every change in a redline to accept, fallback, escalate, human review or novel, with the rule that fired and a verified quote.

- Get escalations approved from a phone in under a minute.

- Prove safety against an LLM-only baseline with numbers.

Non-goals: budget negotiation, drafting new legal language, e-signature, and any real contract or Merck material.

| Metric | Target |
| --- | --- |
| Unsafe accept rate (should escalate, was accepted or countered) | 0 for Siteline on the test set |
| Escalation recall | As high as possible; report it |
| Triage accuracy | Report for Siteline and the baseline |
| Quote pass rate | Near 100% |
| Upload to decision list, 14-change file | Under 30 seconds |

## Requirements

P0 is the demo path and is never cut. P1 adds prize value. P2 is cut first.

| Priority | Requirement | Owner |
| --- | --- | --- |
| P0 | Parse a Word file's tracked insertions, deletions and comments exactly | Duna |
| P0 | Map each change to one of 9 playbook clause types | poppi |
| P0 | Extract values with Claude, each with a verbatim quote, then verify the quote | poppi |
| P0 | Rules engine assigns one outcome per change and logs the rule | poppi |
| P0 | Redline review screen: one card per change with outcome, rule, quote, owner, override with reason | Tined |
| P0 | Approval by Photon text; reply updates the card live | Duna |
| P0 | Eval: Siteline versus LLM-only baseline on about 150 labeled changes | poppi |
| P0 | Demo file (Site 07, 14 changes), playbook and labeled set | khasedd |
| P1 | Parse each upload inside a Daytona sandbox | Duna |
| P1 | Voice call to the approver if the text gets no reply | Duna |
| P1 | Export counter-proposal as Word with comments | Duna |
| P1 | Agreement inbox and portfolio radar | Tined |
| P2 | Chalk Agent Evals for the eval run | poppi |
| P2 | Inbound email: a site emails its redline to the agent | Duna |
| P2 | Playbook editor (else load from JSON) | Duna |

## Sponsor Integrations

| Sponsor | What it does in Siteline | Prize targeted | Fallback |
| --- | --- | --- | --- |
| Photon 2.0 | Approver agent: one iMessage per escalation, reply 1, 2 or 3; calls the approver if no reply | Messaging Agent; best voice agent | Teammate iPhone or on-screen phone |
| Daytona | Each uploaded Word file is parsed in a fresh sandbox, only JSON comes back, then the sandbox is deleted; eval runs in parallel sandboxes | Best Use of Daytona | Local parser behind a flag |
| Chalk | Agent Evals runs the Siteline versus baseline comparison | Best Data-Driven Agent | Own eval harness; drop Chalk if setup passes 1 hour |
| Anthropic (Claude API) | Clause extraction with JSON-schema output and quotes | Main tracks | Cached extraction for the demo file |

Main tracks: Regeneron "Reinvent Clinical Trials" and Best Overall.

## Milestones, Risks and Open Questions

| When | Gate |
| --- | --- |
| Saturday 1 PM | Demo path works end to end: upload, triage, approval text, review screen |
| Saturday 9 PM | P1 done: Daytona parsing, voice fallback, Word export, eval numbers |
| Sunday 4 AM | Feature freeze; rehearsals and backup video |
| Sunday 8 AM | Devpost submitted |

| Risk | Mitigation |
| --- | --- |
| Extraction errors | Quote verification; low confidence goes to human review |
| Texting or calls fail live | Teammate iPhone, on-screen phone, recorded video |
| Sandbox start-up slows the demo | Local parser flag; cached results for the demo file |
| Scope creep from three sponsor prizes | P0 first; P2 cut in listed order |
| Questions about the Merck link | Clean-room rule: public sources only, built this weekend |

Open questions:

- ☐ Can one team win both Photon prizes?

- ☐ Regeneron track requirements (not published yet)

- ☐ Daytona and Chalk credits for the event

- ☐ Publication playbook row: is the 75-day fallback reversed?